## Read me
RESET — test plan
Booking, shop and admin, across web and Android.
How to use this
Work top to bottom. | Sheets are ordered by depth: Smoke first, then each surface, then the business logic that spans them. A failure in Smoke usually explains failures further down, so stop and report it rather than working through the rest.
Fill three columns. | Actual result, Status and Notes. Everything else is the script and should not need editing.
Status values. | Pass / Fail / Blocked / N/A, from the dropdown. Blocked means something else stopped you reaching the check — say what in Notes.
A failure needs three things. | What you did, what you saw, and what you expected. A screenshot of the whole window beats a crop: the URL and the time are usually the clue.
REGRESSION cases. | Marked in the Type column. Each one is a fault that was found and fixed during this build. They are here because a fixed bug nobody re-tests is a bug waiting to come back.
Where to test
Customer website | https://resetmen.in
Admin panel | https://admin.resetmen.in
API | https://api.resetmen.in/api/v1
Android | app-release.apk — v1.0.0+1, signed with the RESET upload key
Sign in
Admin (staff) | admin@resetmen.in / Reset@123
SECURITY | This password is weak and the panel is on the public internet. Change it before the shop opens, and do not circulate this file outside the test team. Anyone with these two lines can read every customer's name and phone number.
Customer | Google sign-in only — there is no password. Use your own Google account, or a throwaway one. Each tester should use a different account: several testers sharing one account will trip the double-booking rule and look like a defect.
The shop as configured today
Store | RESET, Pune. +91 94044 91801.
Opening hours | Tuesday to Sunday, 09:00–21:00. CLOSED MONDAYS — a Monday shows no slots, and that is correct, not a bug.
Booking horizon | 7 days. Nothing further out can be booked.
Free cancellation | Up to 120 minutes before the slot.
Payment | There is NO online payment. Every booking and order is settled at the counter. This is the single most important thing to hold in mind while testing — most of the surprising behaviour follows from it.
Treatments | Head ₹49 / 10 min · Head + Neck + Shoulder ₹99 / 15 min · Head + Neck + Shoulder + Back ₹149 / 20 min · Basic ₹199 / 20 min · Premium ₹299 / 30 min
Stations | Station 1 and 2 perform every treatment. Station 3 performs Head and Head + Neck + Shoulder only. Three customers at a time, at most.
Shop | The product shelf is EMPTY today. Shop cases are marked N/A until the client stocks something — ask before testing them, or add a product yourself under Admin → Products.
What 'booked' means here
Booking is not payment. | A new booking is CONFIRMED for the slot but UNPAID. The customer sees 'Awaiting confirmation' and gets NO QR code. Staff take the money at the counter and press Mark paid, and only then does the entry code appear. A booking that shows no QR is working correctly.
Orders behave the same way. | A shop order is placed as unpaid and reads 'Pay at the store'. It holds its stock until it is paid for or cancelled.

## 1 Smoke
1 · Smoke
Fifteen minutes. If any of these fail, stop and report — the rest of the plan will fail for the same reason.
ID | Area | Priority | Type | Precondition | Steps | Test data | Expected result | Actual result | Status | Notes
SM-01 | Web | P1 | Basic | None | Open https://resetmen.in in a browser. | — | The page loads. Treatments are listed with prices. No error, no blank screen. |  | Not run
SM-02 | Web | P1 | Basic | None | Open https://www.resetmen.in (with the www). | www.resetmen.in | Redirects to https://resetmen.in and loads. REGRESSION: www had no certificate and failed hard for a year via HSTS. |  | Not run
SM-03 | Admin | P1 | Basic | None | Open https://admin.resetmen.in, sign in. | admin@resetmen.in / Reset@123 | Signs in and lands on Today. Nav shows Timeline, Check in, Payments due, Customers, Catalog, Capacity, Rewards, Products, Payments, Reports, Staff, Audit. |  | Not run
SM-04 | API | P1 | Basic | None | Open https://api.resetmen.in/api/v1/health in a browser. | — | Returns a healthy response, not an error page. |  | Not run
SM-05 | Android | P1 | Basic | APK installed | Open the app. Wait for the home screen. | — | Treatments load with prices. Five tabs at the bottom: Book, Visits, Shop, Rewards, You. |  | Not run
SM-06 | Web | P2 | Basic | None | Open https://resetmen.in/robots.txt and /sitemap.xml. | — | Both load. The sitemap lists the homepage, /shop and five /service/ URLs. |  | Not run

## 2 Customer web
2 · Customer — website
Browsing, signing in and booking on https://resetmen.in. Use a Google account nobody else on the team is using.
ID | Area | Priority | Type | Precondition | Steps | Test data | Expected result | Actual result | Status | Notes
CW-01 | Catalogue | P1 | Basic | Signed out | 1. Open the homepage. 2. Read the treatment list. | — | Five treatments, each with a price and a duration. Prices match the Read me sheet. |  | Not run
CW-02 | Catalogue | P2 | Basic | Signed out | 1. Type 'head' into the search field. | head | The list narrows to the head treatments as you type. No page reload. |  | Not run
CW-03 | Catalogue | P2 | Basic | Signed out | 1. Open a treatment. 2. Press the browser Back button. | Premium | Returns to the catalogue in the same scroll position, not to the top of an empty page. |  | Not run
CW-04 | Booking | P1 | Basic | Signed out | 1. Open Head. 2. Choose a time. 3. On the checkout screen, press Book. 4. Sign in with Google when asked. | Head, any open day | Sign-in is asked for BEFORE anything is booked. After signing in the booking completes. |  | Not run
CW-05 | Booking | P1 | REGRESSION | Signed out, Google account with no phone saved | 1. Open Premium. 2. Choose a time. 3. Press Book. 4. Sign in. 5. When asked for a mobile number, enter it and save. 6. DO NOT press Book again. 7. Reload the page. | Premium | NOTHING is booked. Visits is empty. The original fault booked the slot on page load, so a customer who changed their mind already had an appointment. |  | Not run
CW-06 | Booking | P1 | Basic | Signed in, no phone saved | 1. Book any treatment. 2. At the prompt, enter a mobile number. | Any real 10-digit number starting 6-9 | The number is accepted and the booking continues without starting again. |  | Not run
CW-07 | Validation | P2 | Negative | Signed in | 1. At the phone prompt, try each: 12345 · 1234567890 · abcdefghij · 99999999999 | See steps | Each is refused with a readable reason. Only ten digits starting 6–9 is accepted. No crash, no silent acceptance. |  | Not run
CW-08 | Booking | P1 | Basic | Signed in with a phone number | 1. Book Head for any open slot. 2. Read the confirmation screen. | Head | Says 'Awaiting confirmation'. NO QR code. Explains the store will call to confirm and take payment. This is correct — payment happens at the counter. |  | Not run
CW-09 | Booking | P1 | Basic | A booking exists from CW-08 | 1. Open Visits. | — | The booking is listed, marked 'Awaiting confirmation', with the treatment, time and price. |  | Not run
CW-10 | Booking | P1 | Complex | A booking exists | 1. In the admin panel open Payments due. 2. Find the booking and press Mark paid. 3. Back in the customer site, reload Visits and open the booking. | Same booking | It now reads Confirmed and a QR code has appeared. The QR must NOT exist before this step. |  | Not run
CW-11 | Cancellation | P2 | Basic | A booking more than 2 hours away | 1. Open the booking. 2. Cancel it. | — | Asks for confirmation first, then cancels. The slot becomes bookable again. |  | Not run
CW-12 | Account | P2 | Negative | Signed in | 1. Open Account. 2. Clear the mobile number and save. | empty | Refused with a reason. A booking cannot be made without a number, so it cannot be emptied. |  | Not run
CW-13 | Account | P2 | REGRESSION | Signed in | 1. Open Account. 2. Set date of birth to a date in the future and save. | Any future date | Refused. The original fault accepted it — the 13-year rule existed only in the date picker and the API had no check at all. |  | Not run
CW-14 | Account | P3 | Complex | Signed in with at least one upcoming booking | 1. Account → Delete my account. 2. Confirm. 3. Sign in again with the same Google account. | — | The account is emptied and upcoming bookings are CANCELLED, freeing their slots. Signing in again gives a brand-new empty account. REGRESSION: deleted accounts used to leave bookings holding stations, which made the shop look full. |  | Not run
CW-15 | Layout | P2 | Basic | None | 1. Open the site on a phone, or narrow the browser to ~400px. 2. Visit every page. | — | No sideways scrolling anywhere. Buttons reachable. Nothing cut off at the edge. |  | Not run
CW-16 | Layout | P2 | REGRESSION | Signed in | 1. On a phone, trigger a message (for example a failed booking). | — | The message sits ABOVE the bottom navigation and its close button can be tapped. It used to appear behind the nav bar. |  | Not run

## 3 Customer Android
3 · Customer — Android app
app-release.apk, v1.0.0+1. The flow must match the website exactly; where it differs, that is the defect.
ID | Area | Priority | Type | Precondition | Steps | Test data | Expected result | Actual result | Status | Notes
AN-01 | Install | P1 | Basic | APK on the device | 1. Install the APK. 2. Open it. | — | Installs and opens. Home screen lists treatments with prices. |  | Not run
AN-02 | Navigation | P1 | Basic | App open | 1. Tap each of the five tabs. | — | Book, Visits, Shop, Rewards, You all open without error. Shop is NEW in this build. |  | Not run
AN-03 | Booking | P1 | REGRESSION | Signed out | 1. Open a treatment. 2. Pick a time. 3. Look at the checkout screen but DO NOT press Book. 4. Leave the screen. 5. Sign in and open Visits. | Head | NOTHING is booked. The original fault created the booking when the screen opened; signed-out users additionally hit an error they could not recover from. |  | Not run
AN-04 | Booking | P1 | REGRESSION | Signed out | 1. Open a treatment, pick a time. 2. Press Book. | Head | The sign-in sheet appears FIRST. After signing in the booking completes. Previously a signed-out user could not book at all — the button stayed disabled. |  | Not run
AN-05 | Booking | P1 | REGRESSION | Signed in, no phone saved | 1. Press Book. | — | A sheet asks for the mobile number, accepts it and continues the booking. Previously it showed an error message and stopped, with nothing the customer could do. |  | Not run
AN-06 | Booking | P1 | Basic | Signed in with a phone | 1. Book a treatment. 2. Read the confirmation. | Head | 'Awaiting confirmation', a clock icon, NO QR. Wording matches the website. |  | Not run
AN-07 | Booking | P1 | Complex | An unpaid booking exists | 1. Admin → Payments due → Mark paid. 2. In the app, pull to refresh Visits and open it. | — | Now reads Confirmed with a QR code. REGRESSION: the app never read the paid flag, so it told a customer who had already paid that someone would call to take payment. |  | Not run
AN-08 | Offline | P2 | Complex | A PAID booking with a QR | 1. Open the booking so it loads. 2. Turn on aeroplane mode. 3. Reopen the booking. | — | The QR is still shown from the cache, and still marked paid. It must NOT flip to 'Awaiting confirmation' just because the phone is offline. |  | Not run
AN-09 | Offline | P2 | Negative | Aeroplane mode on | 1. Try to book. | — | A clear 'no connection' message. Not a blank screen, not a crash. |  | Not run
AN-10 | Navigation | P2 | Basic | App open | 1. Open a treatment, then a time. 2. Press the Android back button repeatedly. | — | Back moves up one screen at a time. It must not close the app from inside a booking. |  | Not run
AN-11 | Parity | P1 | Complex | Same account on both | 1. Book on the website. 2. Open Visits in the app. 3. Cancel in the app. 4. Reload the website. | — | Both show the same booking, the same status and the same price throughout. A difference either way is a defect. |  | Not run

## 4 Admin
4 · Admin panel
https://admin.resetmen.in. Several of these are regressions from screens that crashed or offered no way to do the thing they were for.
ID | Area | Priority | Type | Precondition | Steps | Test data | Expected result | Actual result | Status | Notes
AD-01 | Access | P1 | Negative | Signed out | 1. Open https://admin.resetmen.in/timeline directly. | — | Redirected to the sign-in screen. The panel must not be reachable signed out. |  | Not run
AD-02 | Access | P1 | Negative | None | 1. Sign in with the right email and a wrong password. | admin@resetmen.in / wrong | Refused with a readable message. No hint about which half was wrong. |  | Not run
AD-03 | Screens | P1 | Basic | Signed in | 1. Open every nav item in turn. | — | Each screen renders. No 'Application error', no blank page. |  | Not run
AD-04 | Tabs | P1 | REGRESSION | Signed in | 1. Capacity → click ALL five tabs: Stations, Allocation rules, Opening hours, Closures, Booking settings. | — | Every tab renders. Allocation rules crashed with a client-side exception on every load before this build. |  | Not run
AD-05 | Tabs | P2 | REGRESSION | Signed in | 1. Catalog → all four tabs. 2. Rewards → all three. 3. Products → both. | — | Every tab renders. Add-ons under Catalog and Closures under Capacity are NEW screens. |  | Not run
AD-06 | Forms | P1 | REGRESSION | Signed in, normal full-screen window | 1. Products → Add product. 2. Without resizing the window, find the Save button. | — | The dialog fits the window and Save is reachable. It used to hang off the bottom of the screen — the fix is not visible unless you check on a full-size window. |  | Not run
AD-07 | Forms | P1 | REGRESSION | Signed in | 1. Repeat AD-06 for: Catalog → Add service, Capacity → Add closure, Rewards → New campaign, Catalog → Add-ons → Add group, Staff → Add. | — | Every dialog fits and every Save button is reachable. This affected every form in the panel, not one screen. |  | Not run
AD-08 | Payments | P1 | Basic | An unpaid booking exists | 1. Open Payments due. | — | Lists the booking with the customer's name, the amount and a tappable phone number. Also shows an 'Shop orders' section for unpaid orders. |  | Not run
AD-09 | Payments | P1 | Complex | An unpaid booking exists | 1. Press Mark paid. 2. Press Mark paid a second time on the same booking. | — | The first records the payment. The second says it was already paid and does NOT double the day's takings. A double-tap at a busy counter must be safe. |  | Not run
AD-10 | Payments | P2 | Basic | An unpaid booking exists | 1. Press Cancel on the row. | — | Asks for confirmation before cancelling. The slot is freed. |  | Not run
AD-11 | Check-in | P1 | Complex | An UNPAID booking exists | 1. Check in → enter the booking code → Check in. | The booking's code | REFUSED, saying it has not been paid for. An unpaid customer must not be able to walk in. |  | Not run
AD-12 | Check-in | P1 | Complex | A PAID booking exists | 1. Check in → enter its code. | The booking's code | Accepted. The booking moves to Checked in. |  | Not run
AD-13 | Catalog | P2 | REGRESSION | Signed in | 1. Catalog → Services. Look at each row. | — | Every row has visible Edit and Delete buttons, and up/down arrows to reorder. None of these existed before — editing was an undeclared click on the row. |  | Not run
AD-14 | Catalog | P2 | Negative | A service with upcoming bookings | 1. Try to delete that service. | — | Refused, and says how many upcoming bookings are in the way. |  | Not run
AD-15 | Capacity | P1 | REGRESSION | Signed in | 1. Capacity → Stations. Read the 'Can perform' column. | — | Shows what each station can actually do — 'Every service', or the named treatments. There is a 'Change services' button on each row. Previously the column was a bare word with no header and staff reported there was no way to assign services. |  | Not run
AD-16 | Capacity | P1 | Complex | Signed in | 1. Capacity → Closures → Add closure. 2. Close the whole store for a day you can test. 3. On the customer site, try to book that day. 4. Lift the closure. | A date within 7 days | No slots are offered on a closed day. Lifting the closure puts them back. NEW screen — this could not be done at all before. |  | Not run
AD-17 | Capacity | P2 | Negative | A booking exists on a given day | 1. Try to close the store over that booking. | — | Refused, naming how many bookings are in the way. Nobody gets stranded by a change made after they booked. |  | Not run
AD-18 | Customers | P2 | REGRESSION | A customer with bookings | 1. Customers → open one. | — | Shows their recent visits AND their wallet. Previously it showed counters only — you could see someone had eight visits and not one of the eight. |  | Not run
AD-19 | Products | P2 | Basic | Signed in | 1. Products → Add product with a price and stock. 2. Edit it. 3. Adjust stock. 4. Delete it. | Name: QA test, ₹100, stock 5 | All four work. Delete asks first. |  | Not run
AD-20 | Audit | P3 | Basic | After doing several of the above | 1. Open Audit. | — | The actions you just took are listed, with who did them and when. |  | Not run

## 5 Business logic
5 · Business logic
The rules that span screens. These are the cases most likely to find something, and the ones worth doing slowly.
ID | Area | Priority | Type | Precondition | Steps | Test data | Expected result | Actual result | Status | Notes
BL-01 | Double booking | P1 | REGRESSION | Signed in with a phone | 1. Book Head (10 min) at, say, 14:00. 2. Now try to book Premium (30 min) at 14:00 as well. | Same time, two treatments | Refused, and the message says it clashes with YOUR OWN booking, naming the treatment and its code. It must NOT say 'that time has just been taken' — that blames a stranger for the customer's own appointment. |  | Not run
BL-02 | Double booking | P1 | Complex | As above | 1. Book Head at 14:00. 2. Book Head again at 14:30. | Non-overlapping times | ALLOWED. Two bookings that do not overlap are legitimate. |  | Not run
BL-03 | Capacity | P1 | Complex | Three testers, or three accounts | 1. Book the SAME time from three different accounts. 2. Try a fourth. | Same slot, four attempts | Three succeed — there are three stations. The fourth is refused. Check the admin Timeline shows three bookings side by side. |  | Not run
BL-04 | Capacity | P1 | Complex | Signed in | 1. Note which treatments Station 3 cannot do (see Read me). 2. Book Premium from three accounts at the same time. | Premium ×3 | Only TWO succeed. Station 3 cannot perform Premium, so only two stations are eligible. This is correct, not a bug. |  | Not run
BL-05 | Horizon | P2 | Negative | Signed in | 1. Try to pick a date more than 7 days ahead. | Day 8+ | Not offered. The calendar stops at the horizon. |  | Not run
BL-06 | Opening hours | P2 | Basic | Signed in | 1. Try to book on a Monday. | Any Monday | No slots. The shop is shut on Mondays — correct behaviour. |  | Not run
BL-07 | Opening hours | P2 | Complex | Signed in | 1. Look at the last slots of a day for Premium (30 min). | Premium, late in the day | No slot is offered that would run past 21:00. A 30-minute treatment cannot start at 20:45. |  | Not run
BL-08 | Pricing | P1 | Complex | Signed in | 1. Open a treatment with add-ons. 2. Tick some. 3. Watch the total. 4. Book. 5. Check the price in Visits and in the admin panel. | Any treatment with add-ons | The total updates as options are ticked, and the SAME figure appears on the confirmation, in Visits and in the admin panel. The server re-prices at booking, so a mismatch is serious. |  | Not run
BL-09 | Pricing | P1 | Complex | A booking exists at a known price | 1. In admin, change that treatment's price. 2. Reload the existing booking. | Change ₹49 → ₹59 | The existing booking keeps the price it was made at. A price change must never rewrite a booking already taken. Put the price back afterwards. |  | Not run
BL-10 | Duration | P2 | Complex | Signed in | 1. Book a treatment WITH an add-on that adds time. 2. In admin, open the Timeline. | — | The block on the timeline is as long as the treatment PLUS the add-on. The station is held for the full time. |  | Not run
BL-11 | Cancellation | P2 | Negative | A booking less than 2 hours away | 1. Try to cancel it. | — | Not offered, or refused with the reason. Free cancellation ends 120 minutes before. |  | Not run
BL-12 | Payment | P1 | Complex | A cancelled booking | 1. In admin, try to Mark paid a booking that was cancelled. | — | Refused. Money cannot be recorded against a cancelled booking. |  | Not run
BL-13 | Rewards | P3 | Complex | An account with a reward in its wallet | 1. Book, applying the reward. 2. Check the price falls. 3. Check the wallet. | — | The discount is applied and the reward is consumed. It cannot be applied twice. |  | Not run
BL-14 | Rewards | P3 | Complex | A customer with an available reward | 1. Admin → Customers → open them → Revoke the reward. 2. Check the customer's wallet. | — | The reward disappears from their wallet. NEW — there was no way to take back a reward granted by mistake. |  | Not run
BL-15 | Shop | P1 | Complex | At least one product in stock | 1. Add a product to the basket and place the order. | Any product | The order succeeds and says to pay at the store. REGRESSION: the site used to show an ERROR while actually placing the order and taking the stock off the shelf. |  | Not run
BL-16 | Shop | P1 | Complex | An order from BL-15 | 1. Admin → Products → Orders. Filter to Unpaid. 2. Mark paid. 3. Mark ready. | — | The order appears as Unpaid, then Paid, then Ready. 'Mark ready' must be refused before it is paid for. |  | Not run
BL-17 | Shop | P2 | Complex | A product with known stock | 1. Note the stock. 2. Order 2. 3. Check the stock. 4. Cancel the order in admin. 5. Check the stock again. | Stock 5, order 2 | Stock falls by 2 when ordered and returns to 5 when cancelled. |  | Not run
BL-18 | Shop | P2 | Negative | A product with stock 1 | 1. Try to order 5 of it. | qty 5 | Refused, saying there is not enough. The shelf must never go negative. |  | Not run
BL-19 | Idempotency | P2 | Complex | Signed in | 1. On the checkout screen, press Book twice quickly. | — | ONE booking is created, not two. Check Visits. |  | Not run
BL-20 | Concurrency | P1 | Complex | Two testers on two devices | 1. Both open the SAME last remaining slot. 2. Both press Book at the same moment. | The last free slot | One succeeds. The other is refused with a clear message and sent back to pick another time. Neither sees a crash, and the slot is not double-booked. |  | Not run

## 6 Edge and negative
6 · Edge cases, security and accessibility
The unpleasant inputs. Nothing here should ever produce a crash, a blank screen, or a technical error message shown to a customer.
ID | Area | Priority | Type | Precondition | Steps | Test data | Expected result | Actual result | Status | Notes
EG-01 | Input | P2 | Negative | Signed in | 1. Put a very long string (500+ characters) into the name field and save. | 500 × 'a' | Refused politely or truncated. No crash, no 500 error. |  | Not run
EG-02 | Input | P2 | Security | Signed in | 1. Put <script>alert(1)</script> into the name field. 2. Save and view it wherever the name appears, including the admin panel. | <script>alert(1)</script> | Displayed as literal text. NO alert box anywhere, especially not in the admin panel. |  | Not run
EG-03 | Input | P2 | Security | Signed in | 1. Put an emoji and non-Latin text in the name: 'नमस्ते 🙏'. | नमस्ते 🙏 | Saved and displayed correctly on every screen, including the admin panel. |  | Not run
EG-04 | URLs | P2 | Negative | None | 1. Visit /service/not-a-real-thing 2. Visit /booking/00000000-0000-0000-0000-000000000000 | See steps | A proper not-found page. Not a blank screen and not a technical error. |  | Not run
EG-05 | Security | P1 | Security | Two customer accounts, A and B | 1. As A, book something and copy the booking URL. 2. Sign in as B and open that URL. | A's booking URL | B CANNOT see A's booking. This is the most important case on this sheet. |  | Not run
EG-06 | Security | P1 | Security | Signed in as a customer | 1. Open https://admin.resetmen.in with the customer account. | — | Refused. A customer account must not reach the admin panel. |  | Not run
EG-07 | Session | P2 | Complex | Signed in on web | 1. Sign in. 2. Leave the tab for a long period, or clear site data. 3. Try to book. | — | Either still works, or asks to sign in again cleanly. It must not fail silently or lose the booking halfway. |  | Not run
EG-08 | Browser | P2 | Basic | None | 1. Run the smoke sheet in Chrome, Safari (iPhone) and one Android browser. | — | Same behaviour on all three. Note any difference. |  | Not run
EG-09 | Accessibility | P3 | Basic | None | 1. Navigate the booking flow using only the Tab and Enter keys. | — | Every control is reachable and the focused element is always visible. |  | Not run
EG-10 | Accessibility | P3 | Basic | None | 1. Set the phone's font size to the largest setting. 2. Open the app and the site. | — | Text remains readable and nothing is cut off or overlapping. |  | Not run
EG-11 | Performance | P3 | Basic | None | 1. Load the homepage on a normal mobile connection. | — | Usable within a few seconds. Note anything that feels slow. |  | Not run
EG-12 | Data | P2 | Complex | Admin | 1. Reports → run each report for a range covering your test bookings. | — | The figures match what you actually did. Paid bookings count towards revenue; unpaid and cancelled ones do not. |  | Not run

## 7 Defect log
7 · Defect log
One row per defect. Severity: Blocker (cannot continue) · Major (feature unusable) · Minor (works, wrong) · Cosmetic. Attach the whole window, not a crop — the URL and the clock are usually the clue.
Defect ID | Test case | Date | Found by | Surface | Severity | Summary | Steps to reproduce | Expected | Actual | Screenshot | Status